## Sheet1
Week | Tasks | T-shrt size | Quarter | Tasks | Year | Tasks
2020-10-01 | Set up local server and setup.py | M | 1 | Build a micro-service to predict ML model result | 2022 | Build a highly availabe/scalable/reliable ML model prediction service.
2020-10-08 | Set up the Docker file working locally | M | 2 | Add an integration to 3rd party datasets
2020-10-15 | Set up the qa/prod server | L | 3 | Add rate limiter to the service to avoid scam
2020-10-22 | Detailed API schema design | L | 4 | Add monitoring/logging system to improve the service
2020-10-29 | Set up swagger UI locally | M
2020-11-05 | Develope Request validation logics | M
2020-11-12 | Develope business logics on APIs | L
2020-11-19 | Develope business logics on APIs | L
2020-11-26 | Build spread sheet for Bug Safari | M
2020-12-03 | Team meeting to test all endpoints | M
2020-12-10 | Build terraform file to scare services | M
2020-12-17 | Pressure test on hotspots Endpoints | L
Goals
Build a web server to predict the ML model result